## HighLevel workplan
Milestone | From | To | Activity | Outputs | Responsible
September - Januray
| 6.10.2010 | 9.10.2010 | Kick-off meeting | Objectives, workplan, monitor, dissem., evaluation plan | All partners
Project started
ICT and language training for elderely people
| 1.10.2010 | 31.1.2011 | ICT and language training for Seniors/ preparation for the project meeting | PPPs - ICT and language courses for seniors/ methodology or case study | All partners
| 1.11.2010 | 20.12.2010 | Creating of logo | Different logos to choose at January meeting | Czech republic
| 1.11.2010 | 30.11.2010 | Creation of wiki web page and facebook | web page, facebook page | Czech republic, Italy
| January 2011 |  | 2nd International meeting Italy | PPPs - ICT and language courses for seniors/ methodology or case study | All partners
1st project review
Present x Past - the changes of the local community
| 1.10.2010 | 30.6.2011 | Past and Present – the changes of the local community, forms of PPPs. The first part of the memory book- Chapter 1 - About the town (local community) - changes in times. | PPPs | All partners
|  | 1.6.2011 | Evaluation forms for participants | Evaluation forms | Czech republic
| June 2011 |  | 3rd International meeting Greece | Past x Present - presentations of materials for the Memory book (Chapter 1) | All partners
2nd project review
(Social) activities for elderely people and activities for the Inter.generation communication
| 1.10.2010 | 31.1.2012 | Social and Inter-generation activities | Map of activities, web content | All partners
| 1.10.2010 | 30.9.2011 | Memory book - Chapter 2 - Family celebrations and weddings | PPPs | All partners
| 1.10.2010 | 30.9.2011 | Preparation for the meeting | Activities for seniors and collecting memories for the Book. | All partners
| October 2011 |  | 4th International meeting Bulgaria | Presentation of senior activities, Memory book Chapter 2 | All partners
3rd project review
Present x Past - the changes of the local community - 1st May and other anniversaries
| 1.10.2010 | 30.12.2011 | Past and Present – the changes of the local community - 1st May and other anniversaries - Memory book chapter 3. Memory book chapter 4 - war memories - optional chapter of the book. | PPPs, videos, recordings | All partners
| January 2012 |  | 5th International meeting France | Memory book - chapter 3 and 4 (optional) | All partners
4th project review
Project monitoring, dissemination, evaluation
| 1.10.2010 | 30.6.2012 | Dissemination - each partner organization, monitoring and evaluation - project meetings, evaluation forms, web, Yahoo group etc. | meeting minutes, workplan, evaluation forms and media articles etc. | All partners
|  | 1.6.2012 | Evaluation forms for participants | Evaluation forms | Czech republic
5th project review
| June 2012 |  | 6th International meeting Finland | Final report, Memory book | All partners

## next Steps OctJan
October 2010 - January 2011
Number | Activity | From | To | Outputs | Responsible
1. | Kick-off meeting | 2010-10-06 | 2010-06-09 | Objectives, workplan, monitoring, diss. and evaluation plan | All partners
2. | ICT training for seniors/ Language training for seniors | 2010-10-01 | 2011-01-31 | ICT and language courses | All partners
3. | Web page (at wiki space) | 2010-11-01 | 2010-11-30 | Webpage | Czech republic
5. | Logo creation | 2010-11-01 | 2010-12-20 | Examples of project logo | Czech republic
9. | Facebook page | 2010-11-01 | 2011-01-15 | Facebook page | Italy
10. | Dissemination - Information for the Chambre of Commerce | 2010-11-01 | 2011-06-30 | Info material fo the Chambre | France
11. | Dissemination - The Press Book - all partners send the names, pictures and e-mails of their national team to the French partner | 2010-11-01 | 2011-06-30 | Press book | France
12. | Preparation for the project meeting | 2010-11-02 | 2011-01-16 | PPPs - ICT and language training for senior citizens - approach: methodology or case study | All partners
13. | 2nd project meeting Italy | 2011-01-19 | 2011-01-22 | Meeting outputs | All partners

## February-June
Number | Activity | From | To | Outputs | Responsible | Tasks
1. | Italy meeting | 2011-01-19 | 2011-01-22 | "ICT and langiage training for seniors - best practice" - experience and knowledge sharing | All partners
2. | ICT training for seniors/ Language training for seniors | 2010-10-01 | 2011-06-30 | ICT and language courses | All partners | Courses production
3. | Web page (at wiki space) | 2010-11-01 | 2011-02-15 | Webpage | Czech republic | Creation of the page
5. | Logo creation | 2010-11-01 | 2011-02-15 | Examples of project logo | Czech republic | Creation of logo
9. | Facebook page | 2010-11-01 | 2011-01-15 | Facebook page | Italy | Italy
10. | Dissemination - Information for the Chambre of Commerce | 2010-11-01 | 2011-06-30 | Info material fo the Chambre | France | Info to Chambre
11. | Dissemination - The Press Book - all partners send the names, pictures and e-mails of their national team to the French partner | 2010-11-01 | 2011-06-30 | Press book | France | Excel frame
12. | International evaluation |  | 2011-05-30 | Evaluation forms | Coordinator | Form to be filled by each partner
13. | National evaluation |  | 2011-06-30 | reporst | All partners | reports to be presented at the 2nd meeting
14. | Dissemination |  | 2011-06-30 | reports, artices etc to be brought to the Greek meeting | All partners | Dissemination outputs to be brought to the meeting
15. | Preparation for the second meeting | 2011-01-25 | 2011-01-16 | Memory book - Chapter 1 - About the town and local area | All partners | PPPs Memory book Chapter 1, maximum 10 slides
16. | 2nd project meeting Italy | 2011-01-19 | 2011-01-22 | Meeting outputs | All partners | All partners

## SeptJan
Number | Activity | From | To | Outputs | Responsible | Tasks
1. | ICT training for seniors/ Language training for seniors and other activities | 2011-09-01 | 2012-01-31 | ICT and language courses, activities for seniors | All partners | Courses production
2. | 4th meeting Bulgaria | 2011-10-26 | 2011-10-29 | 2nd chapter of the Memory book - family ceremonies and weddings | All partners | partner meeting
3. | Creation of presentations - chapter 3 and 4 of the memory book | 2011-11-01 | 2012-01-25 | Webpage | All partners | partner work
5. | 5th meeting France | 2012-01-25 | 2012-01-28 | Chapter 3,4 | All partners | partner meeting
9. | format of the memory book | 2011-11-01 | 2011-12-31 | Memory book format proposal | Czech republic | partner work

## Feb.-June 2012
Number | Activity | From | To | Outputs | Responsible | Tasks
1. | ICT training for seniors/ Language training for seniors and other activities | 2011-09-01 | 2012-06-30 | ICT and language courses, activities for seniors | All partners | Courses production
2. | 5th meeting France | 2012-01-25 | 2012-01-28 | 3nd chapter of the Memory book - family ceremonies and weddings | All partners | partner meeting
3. | Memory book structure - suggestion for the presentation of each partner | 2012-01-01 | 2012-02-15 | Suggestions for the Memory book | Coordinator | Coordinator work
5. | Memory book processed topics | 2012-02-15 | 2012-03-30 | processed topics for the Memory book | All partners | partner work
9. | Memory book -final version | 2012-04-01 | 2012-04-30 | Memory book for Finland meeting | Czech republic | coordinator work
9. | Final evaluation to be sent to all partners |  | 2012-05-30 | Fevaluation form | Czech republic | coordinator work
9. | Final evaluation |  | 2012-06-15 | Evaluation report | Czech republic | coordinator work
9. | Final report |  | 2012-05-31 | Report proposal to be discussed at the project meeting in Finland | Czech republic | coordinator work

## Meeting schedule
MEETING SCHEDULE
PLACE OF THE MEETING | DATE OF THE MEETING | TOPIC OF THE MEETING | FORM OF THE MEETING
Italy | 19.-22.1.2011 | ICT courses for seniors, Language courses for Seniors (methodology and case study) | Project partner meeting
Greece | 29.6.-2.7.2011 | Chapter 1 of the Memory book | Project partner meeting
Bulgaria | 26.-29.10.2011 | Chapter 2 of the Memory book | Project partner meeting
France | 25.-28.1.2012 | Chapter 3 and chapter 4 | Project partner meeting
Finland | 26.-29.6.2012 | Memory book correction and Final report | Project partner meeting